## Product Catalog
Project Name | E-Commerce
StakeHolders/Customers/Users | abc/xyz/zxc etc.
Created By | Yashwanth
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Criteria
For an application to launch,the highest busiiness value will be when the user is able to use the application in a flexible way. | US001 | create a master list of all the users and the products | as an administrator, I want to have have an option create list of users and products . | New
| US002 | view the list of all the created users and products. | as an administrator, I want to have an option to view the list of all created users and products by id or all of them at once and also able to search them . | New
| US003 | delete the list of products and the products. | as an administrator, I want to delete the list of created users and products by id. | New
| US004 | map the products to users and report them by date and category. | as an administartor, I want to have an option to map the purchased products to the users and report them by date and category. | New
| US005 | able to change or reset my password. | as an administrator,I want to have an option to change or update my password. | New

## Sprint Planning
Project Name | E-Commerce
Scrum Team | Dev, QA, PO, Scrum Master etc.
Created By | Yashwanth
Epic | User Story ID | Feature/Title | User Story | Story Points | Sprint
For an application to launch,the highest busiiness value will be when the user is able to use the application in a flexible way. | US001 | create a master list of all the users and the products | as an administrator, I want to have have an option create list of users and products . | 5 | 1
| US002 | view the list of all the created users and products. | as an administrator, I want to have an option to view the list of all created users and products by id or all of them at once and also able to search them . | 5 | 1
| US003 | delete the list of products and the users. | as an administrator, I want to delete the list of created users and products by id. | 5 | 2
| US004 | map the products to users and report them by date and category. | as an administartor, I want to have an option to map the purchased products to the users and report them by date and category. | 5 | 3
| US005 | able to change or reset my password. | as an administrator,I want to have an option to change or update my password. | 8 | 4